## Explications
New? | Steps | Description
64 bits compilation:
- Verify that the dependancy libraries are compiled with the 64 bits platform (configuration x64-Debug and x64-Release)
- Fix 64 bits compilation errors (Debug and Release)
- Verify the project still compile with the 32 bits platform
PVS Studio (https://www.viva64.com/en/pvs-studio/) :
|  | - Scan the project with options: High, Medium, 64 Bits | Start C:\Program Files (x86)\PVS-Studio\Standalone.exe
Select menu Tools->Analyze Your Files (C/C++), and click the Start Monitoring button
Build the project in 64 bits
Click the Stop Monitoring button (small window at the bottom right of the screen)
- Fix the 64 bits High (do not ignore)
- Do a small check of the 64 bits Medium (not mandatory to fix them all)
Unit tests if any
- Build and run the tests (32 and 64 bits in release and debug)
- Fix errors
Final validation:
- Compile in debug and release 32 bits
- Compile in debug and release 64 bits
- Scan with PVS Studio for a last check
Code Review:
- Pull request
Release and tests
- Ask an architect for the regression tests according to the modified libraries

## Checklist
La librairie externe d'Opteon est encore en 32 bits, il faudra faire une mise à jour à la version 5.0 pour utiliser la librairie en 64 bits
|  | % Done | 70.72% | 69.82% | 68.57% | 61.71% | 37.39% | 37.39% | La librairie externe "RFID-eMindTek" est encore en 32 bits, il faudra demander la version 64 bits ou tenter de compiler le code source en 64 bits
Project | Owner | Reviewer | Compilation 64 bits | PVS Studio | Tests Unitaires | Validation finale | Code Review | Build | Notes
LogLib | Mikael |  | Done | Done | N/A | Done | Done | Done | Pull request #1 "Feature/64bits base lib". On prévoit d'utiliser SpeedLog, mais en attendant LogLib est une librairie vide juste pour compiler en 64 bits
LogLib_SimpleManager | Mikael |  | Done | Done | Done | Done |  |  | A besoin de Loglib(Speedlog)
LogLibUnitTest | Mikael |  | Done | Done | Done | Done |  |  | Crash at testTooLongLog when lauching test in debug, location TestAbi.cpp line 45
LogLibUI | Mikael |  | Done | Done | Done | Done |  |  | N'existe plus avec SpeedLog
MainTestLauncher | Vincent | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #1 "Feature/64bits base lib"
TestMainTestLauncher | Vincent | Kevin | Done | Done | Done | Done | Done | Done | Pull request #1 "Feature/64bits base lib"
TestMainTestLauncherScopedInitializer | Vincent | Kevin | Done | Done | Done | Done | Done | Done | Pull request #1 "Feature/64bits base lib"
OptelExceptions | Benoit | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #1 "Feature/64bits base lib"
TextManagement | Vincent | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #1 "Feature/64bits base lib"
TestTextManagement | Vincent | Kevin | Done | Done | Done | Done | Done | Done | Pull request #1 "Feature/64bits base lib"
TestOptelExceptions | Benoit | Kevin | Done | Done | Done | Done | Done | Done | Pull request #1 "Feature/64bits base lib"
OptelExceptions-static | Benoit | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #1 "Feature/64bits base lib"
TextManagement-static | Benoit | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #1 "Feature/64bits base lib"
OptelExceptions-vision | Benoit | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #1 "Feature/64bits base lib"
TextManagement-vision | Benoit | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #1 "Feature/64bits base lib"
Agelena | Benoit |  | Done | Done | N/A |  |  |  | Arrachnida? Va être remplacer?
Acari | Benoit |  | Done | Done | N/A |  |  |  | Arrachnida? Va être remplacer?
Scorpion | Benoit |  | Done | Done | N/A |  |  |  | Arrachnida? Va être remplacer?
Spin | Benoit |  | Done | Done | N/A |  |  |  | Arrachnida? Va être remplacer?
Nemastomoididae | Benoit |  | Done | Done | N/A |  |  |  | Arrachnida? Va être remplacer?
Test_Acari | Kevin |  | Done | Done | In Progress |  |  |  | Arrachnida? Va être remplacer?
Test_Agelena | Kevin |  | Done | Done | Done | Done |  |  | Arrachnida? Va être remplacer?
Test_Scorpion | Kevin |  | Done | Done | Done | Done |  |  | Arrachnida? Va être remplacer?
Test_Spin | Kevin |  | Done | Done | Done | Done |  |  | Arrachnida? Va être remplacer?
Altova | Vincent | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #1 "Feature/64bits base lib"
AltovaXML | Vincent | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #1 "Feature/64bits base lib"
Threads | Benoit |  | Done | Done | N/A | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Network | Benoit |  | Done | Done | N/A | Done |  |  | UDPSocket => boost::asio
Registry | Benoit | Benoit | Done | Done | N/A | Done | Done | Done | Pull request #4 "Feature/64bits registry crypto time transaction SQLite"
FileAlterationMonitor | Benoit |  | Done | Done | N/A | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
Contract | Benoit |  | Done | Done | N/A | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Crypto | Kevin | Benoit | Done | Done | N/A | Done | Done | Done | Pull request #4 "Feature/64bits registry crypto time transaction SQLite"
Utilities | Benoit |  | Done | Done | Done | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
CBridge | Benoit |  | Done | Done | N/A | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Doc_CBridge_Implementor | Benoit |  | Done | Done | N/A | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Time | Benoit | Benoit | Done | Done | N/A | Done | Done | Done | Pull request #4 "Feature/64bits registry crypto time transaction SQLite"
Transaction | Kevin | Benoit | Done | Done | N/A | Done | Done | Done | Pull request #4 "Feature/64bits registry crypto time transaction SQLite"
XML | Benoit |  | Done | Done | N/A | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Spooler | Benoit |  | Done | Done | N/A | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Test_CBridge | Benoit |  | Done | Done | Done | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Test_Contract | Benoit |  | Done | Done | Done | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Test_Crypto | Kevin | Benoit | Done | Done | Done | Done | Done | Done | Pull request #4 "Feature/64bits registry crypto time transaction SQLite"
Test_Network | Kevin |  | Done | Done | Done | Done |  |  | ACE vendor lib: V114 error in PVS studio
Test_Registry | Kevin | Benoit | Done | Done | Done | Done | Done | Done | Pull request #4 "Feature/64bits registry crypto time transaction SQLite". No tests are run when running executable?
Test_Spooler | Kevin |  | Done | Done | Done | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Test_Threads | Kevin |  | Done | Done | Done | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Test_Time | Vincent | Benoit | Done | Done | Done | Done | Done | Done | Pull request #4 "Feature/64bits registry crypto time transaction SQLite"
Test_Transaction | Vincent | Benoit | Done | Done | Done | Done | Done | Done | Pull request #4 "Feature/64bits registry crypto time transaction SQLite"
Test_Utilities | Mikael |  | Done | Done | Done | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
Test_Utilities_GTest | Mikael |  | Done | Done | Done | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
Contract-static | Benoit |  | Done | Done | N/A | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Spooler-static | Benoit |  | Done | Done | N/A | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Utilities-static | Kevin |  | Done | Done | N/A | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
Threads-static | Benoit |  | Done | Done | N/A | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Contract-vision | Benoit |  | Done | Done | N/A | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Spooler-vision | Benoit |  | Done | Done | N/A | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
Utilities-vision | Kevin |  | Done | Done | N/A | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
Threads-vision | Benoit |  | Done | Done | N/A | Done | Done | Done | Pull request #2 "Feature/64bits threads contract cbridge spooler xml"
SQLite | Benoit | Benoit | Done | Done | N/A | Done | Done | Done | Pull request #4 "Feature/64bits registry crypto time transaction SQLite"
TestSQLite | Vincent | Benoit | Done | Done | Done | Done | Done | Done | Pull request #4 "Feature/64bits registry crypto time transaction SQLite"
Parameters | Kevin | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #5 "Feature/64bits parameters visionParameters uiBase genericWidgets".
Test_Parameters | Kevin | Kevin | Done | Done | Done | Done | Done | Done | Pull request #5 "Feature/64bits parameters visionParameters uiBase genericWidgets"
VisionParameters | Kevin | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #5 "Feature/64bits parameters visionParameters uiBase genericWidgets"
UiBase | Vincent | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #5 "Feature/64bits parameters visionParameters uiBase genericWidgets"
GenericWidgets | Vincent | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #5 "Feature/64bits parameters visionParameters uiBase genericWidgets"
GenericWidgetsTest | Vincent | Kevin | Done | Done | Done | Done | Done | Done | Pull request #5 "Feature/64bits parameters visionParameters uiBase genericWidgets"
GenericWidgetsGTest | Vincent | Kevin | Done | Done | Done | Done | Done | Done | Pull request #5 "Feature/64bits parameters visionParameters uiBase genericWidgets"
Remote | Kevin | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #6 "Feature/64bits Remote RemoteMessages TinyXML Identifiers PythonLib"
TestRemote | Kevin | Kevin | Done | Done | Done | Done | Done | Done | Pull request #6 "Feature/64bits Remote RemoteMessages TinyXML Identifiers PythonLib"
RemoteMessages | Kevin | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #6 "Feature/64bits Remote RemoteMessages TinyXML Identifiers PythonLib".
TestRemoteMessages | Vincent | Kevin | Done | Done | Done | Done | Done | Done | Pull request #6 "Feature/64bits Remote RemoteMessages TinyXML Identifiers PythonLib"
TinyXML | Benoit | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #6 "Feature/64bits Remote RemoteMessages TinyXML Identifiers PythonLib"
GenericFactory | Kevin |  | Done | Done | N/A | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
GenericFactoryTests | Kevin |  | Done | Done | Done | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
GenericFactory-static | Kevin |  | Done | Done | N/A | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
GenericFactory-vision | Kevin |  | Done | Done | N/A | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
Identifiers | Kevin | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #6 "Feature/64bits Remote RemoteMessages TinyXML Identifiers PythonLib"
Test_Identifiers | Vincent | Kevin | Done | Done | Done | Done | Done | Done | Pull request #6 "Feature/64bits Remote RemoteMessages TinyXML Identifiers PythonLib"
TransportLayers | Kevin |  | Done | Done | N/A |  |  |  | boost::asio!
TransportLayersUT | [8 empty] | boost::asio!
VirtualPrinter |  |  |  |  | N/A |  |  |  | Removed from PP solution
NBC |  |  |  |  | N/A |  |  |  | Laisser en 32 bits
NBC-UDP |  |  |  |  | N/A |  |  |  | Laisser en 32 bits
Configuration |  |  |  |  | N/A |  |  |  | What's that?
Test_NBC | [8 empty] | Laisser en 32 bits
Test_NBC-UDP | [8 empty] | Laisser en 32 bits
PythonLib_Unit_Tests | Vincent | Kevin | Done | Done | Done | Done | Done | Done | Pull request #6 "Feature/64bits Remote RemoteMessages TinyXML Identifiers PythonLib"
PythonLib | Kevin | Kevin | Done | Done | N/A | Done | Done | Done | Pull request #6 "Feature/64bits Remote RemoteMessages TinyXML Identifiers PythonLib"
TestPythonLib | Vincent | Kevin | Done | Done | Done | Done | Done | Done | Pull request #6 "Feature/64bits Remote RemoteMessages TinyXML Identifiers PythonLib"
LabelLayout | Kevin | Benoit | Done | Done | N/A | Done | Done | Done | Pull request #7 "Feature/64bits LabelLayout TrailFileSchema TrailLib21Cfr11 Security".
LabelLayoutConfiguration | Kevin | Benoit | Done | Done | N/A | Done | Done | Done | Pull request #7 "Feature/64bits LabelLayout TrailFileSchema TrailLib21Cfr11 Security"
Coders-static | Kevin |  | Done | Done | N/A |  |  |  | Same as Coders
Unescape | Vincent | Benoit | Done | Done | N/A | Done | Done | Done | Pull request #7 "Feature/64bits LabelLayout TrailFileSchema TrailLib21Cfr11 Security"
LabelLayout_Unit_Tests | [8 empty] | Besoin de Transport Layers
Coders_Unit_Tests | [8 empty] | Besoin de Transport Layers
Test_LabelLayout | Vincent | Benoit | Done | Done | Done | Done | Done | Done | Pull request #7 "Feature/64bits LabelLayout TrailFileSchema TrailLib21Cfr11 Security"
Coders | Kevin |  | Done | Done | N/A |  |  |  | A besoin de TransportLayers
TrailLib21Cfr11 | Kevin | Benoit | Done | Done | N/A | Done | Done | Done | Pull request #7 "Feature/64bits LabelLayout TrailFileSchema TrailLib21Cfr11 Security".
TrailFileSchema | Vincent | Benoit | Done | Done | N/A | Done | Done | Done | Pull request #7 "Feature/64bits LabelLayout TrailFileSchema TrailLib21Cfr11 Security"
TestTrailLib21Cfr11 | Vincent | Benoit | Done | Done | Done | Done | Done | Done | Pull request #7 "Feature/64bits LabelLayout TrailFileSchema TrailLib21Cfr11 Security"
Security | Kevin | Benoit | Done | Done | N/A | Done | Done | Done | Pull request #7 "Feature/64bits LabelLayout TrailFileSchema TrailLib21Cfr11 Security"
Test_Security | Vincent | Benoit | Done | Done | Done | Done | Done | Done | Pull request #7 "Feature/64bits LabelLayout TrailFileSchema TrailLib21Cfr11 Security"
Plugin | Kevin |  | Done | Done | N/A | Done |  |  | Pull request #8 "Feature/64bits Plugin RemoteServices ImageLib Cameras"
PluginTests | Vincent |  | Done | Done | Done | Done |  |  | Pull request #8 "Feature/64bits Plugin RemoteServices ImageLib Cameras"
PluginTestModule | Vincent |  | Done | Done | Done | Done | Done | Done | A ete enlever du Mono_repo Author Benoit Jousson , commit date 26/7/2017 commit hash: 7e81a3287adb8e5dfb42e74af0835b0c616fcdb4
RemoteServices | Kevin |  | Done | Done | N/A | Done |  |  | Pull request #8 "Feature/64bits Plugin RemoteServices ImageLib Cameras"
RemoteServicesTests | Benoit |  | Done | Done | Done | Done |  |  | Pull request #8 "Feature/64bits Plugin RemoteServices ImageLib Cameras"
VirtualHandheld | Vincent |  | Done | Done | N/A | In Progress |  |  | Besoin de Transport Layers
Handhelds | Vincent |  | Done | Done | N/A | In Progress |  |  | Besoin de Transport Layers
HandheldsGui | Vincent |  | Done | Done | N/A |  |  |  | Besoin de Transport Layers
HandheldsPlugin | Vincent |  | Done | Done | N/A |  |  |  | Besoin de Transport Layers
TestHandheldGui | Vincent |  | Done | [5 empty] | Besoin de Transport Layers
TestHandhelds | Vincent |  | Done | [5 empty] | Besoin de Transport Layers
ImageLib | Benoit |  | Done | Done | N/A | Done |  |  | Pull request #8 "Feature/64bits Plugin RemoteServices ImageLib Cameras"
Test_ImageLib | Benoit |  | Done | Done | Done | Done |  |  | Pull request #8 "Feature/64bits Plugin RemoteServices ImageLib Cameras"
Cameras | Benoit |  | Done | Done | N/A | Done |  |  | Pull request #8 "Feature/64bits Plugin RemoteServices ImageLib Cameras"
Test_Cameras | Benoit |  | Done | Done | Done | Done |  |  | Pull request #8 "Feature/64bits Plugin RemoteServices ImageLib Cameras"
Opteon |  |  |  |  | N/A |  |  |  | Besoin de Opteon 3rd party 64 bits
Test_Opteon | [8 empty] | Besoin de Opteon 3rd party 64 bits
VirtualCam |  |  |  |  | N/A |  |  |  | A besoin de Network
VirtualCamTest | [8 empty] | A besoin de Network
VirtualCamGui |  |  |  |  | N/A |  |  |  | A besoin de Network
VirtualCamGuiTest | [8 empty] | A besoin de Network
JAI |  |  |  |  | N/A |  |  |  | Pull request #15
Enumerate_JAI |  |  |  |  | N/A |  |  |  | Pull request #15
SimCam |  |  |  |  | N/A |  |  |  | Pull request #16
Test_SimCam | [8 empty] | Pull request #16
SimCamRemoteCommand |  |  |  |  | N/A |  |  |  | Pull request #16
VisionCamController |  |  |  |  | N/A |  |  |  | Pull request #17
VisionCamControllerGui |  |  |  |  | N/A |  |  |  | Pull request #17
VisionCamControllerGuiTest | [8 empty] | Pull request #17
VisionCamControllerTests | [8 empty] | Pull request #17
BundleInspector | Kevin |  | Done | Done | N/A | Done |  |  | Pull request #9 "Feature/64bits BundleInspector LogicalCam SerializationComponent"
BundleInspectorControlLib | Kevin |  | Done | Done | N/A | Done |  |  | Pull request #9 "Feature/64bits BundleInspector LogicalCam SerializationComponent"
BundleInspectorGui | Kevin |  | Done | Done | N/A | Done |  |  | Pull request #9 "Feature/64bits BundleInspector LogicalCam SerializationComponent"
BundleInspectorClrFacade | Kevin |  | Done | Done | N/A | Done |  |  | Pull request #9 "Feature/64bits BundleInspector LogicalCam SerializationComponent"
BundleInspectorClientTest | Kevin |  | Done | Done | N/A | Done |  |  | Pull request #9 "Feature/64bits BundleInspector LogicalCam SerializationComponent"
LogicalCam | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #9 "Feature/64bits BundleInspector LogicalCam SerializationComponent"
LogicalCamTests |  |  | - | [5 empty] | Done? À vérifier
SerializationComponent | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #9 "Feature/64bits BundleInspector LogicalCam SerializationComponent"
SerializationComponentLoader | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #9 "Feature/64bits BundleInspector LogicalCam SerializationComponent"
SerializationComponentTestApplication | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #9 "Feature/64bits BundleInspector LogicalCam SerializationComponent"
SerializationComponentTestApplication2 | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #9 "Feature/64bits BundleInspector LogicalCam SerializationComponent"
MultipleInspectionComponentTestApplication | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #10 "Feature/64bits MultipleInspectionComponent ServiceInterfaces ServiceUsers MiniLCD"
MultipleInspectionComponent | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #10 "Feature/64bits MultipleInspectionComponent ServiceInterfaces ServiceUsers MiniLCD"
MultipleInspectionComponentLoader | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #10 "Feature/64bits MultipleInspectionComponent ServiceInterfaces ServiceUsers MiniLCD"
AlarmsLib |  |  | - |  | N/A |  |  |  | Pull request #14
AlarmsUI |  |  | - |  | N/A |  |  |  | Pull request #14
AlarmsUnitTests | [8 empty] | Pull request #14
OptelPasswordChanger | Vincent |  | Done | Done | N/A |  |  |  | Pull request #15
IOActionsLib | Vincent |  | Done | Done | N/A |  |  |  | Pull request #15
ServiceInterfaces | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #10 "Feature/64bits MultipleInspectionComponent ServiceInterfaces ServiceUsers MiniLCD"
ServiceUsers | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #10 "Feature/64bits MultipleInspectionComponent ServiceInterfaces ServiceUsers MiniLCD"
ServiceUsersPlugin | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #10 "Feature/64bits MultipleInspectionComponent ServiceInterfaces ServiceUsers MiniLCD"
ServiceUsersTests | Vincent |  | Done | Done | Done | Done |  |  | Pull request #10 "Feature/64bits MultipleInspectionComponent ServiceInterfaces ServiceUsers MiniLCD"
MiniLCDServiceTest | Vincent |  | Done | Done | Done | Done |  |  | Pull request #10 "Feature/64bits MultipleInspectionComponent ServiceInterfaces ServiceUsers MiniLCD"
MiniLCDPlugin | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #10 "Feature/64bits MultipleInspectionComponent ServiceInterfaces ServiceUsers MiniLCD"
MiniLCD | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #10 "Feature/64bits MultipleInspectionComponent ServiceInterfaces ServiceUsers MiniLCD". Bloquant: Parameters errors shown in release 64 bits but it build correctly on its own / release 64 bits/ Scan
MiniLCDGui | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #10 "Feature/64bits MultipleInspectionComponent ServiceInterfaces ServiceUsers MiniLCD"
VirtualLCD | Vincent |  | Done | Done | N/A |  |  |  | C# WPF
LineMasterService | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #11 "feature/64bits_lineMasterService_lineMasterServicePlugin_CheckWeigher_checkWeigherPlugin_manualInspectionPlugin"
LineMasterServicePlugin | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #11 "feature/64bits_lineMasterService_lineMasterServicePlugin_CheckWeigher_checkWeigherPlugin_manualInspectionPlugin"
CheckWeigherPlugin | Kevin |  | Done | Done | N/A | Done |  |  | Pull request #11 "feature/64bits_lineMasterService_lineMasterServicePlugin_CheckWeigher_checkWeigherPlugin_manualInspectionPlugin"
CheckWeigher | Kevin |  | Done | Done | N/A | Done |  |  | Pull request #11 "feature/64bits_lineMasterService_lineMasterServicePlugin_CheckWeigher_checkWeigherPlugin_manualInspectionPlugin"
CheckWeigherTests | Vincent |  | Done | Done | Done | Done |  |  | Pull request #11 "feature/64bits_lineMasterService_lineMasterServicePlugin_CheckWeigher_checkWeigherPlugin_manualInspectionPlugin"
Sliders | Kevin |  | Done | Done | N/A |  |  |  | A besoin de TransportLayers
SlidersPlugin | Kevin |  | Done | Done | N/A |  |  |  | A besoin de Sliders
SlidersGui |  |  |  |  | N/A |  |  |  | A besoin de Sliders
ManualInspectionPlugin | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #11 "feature/64bits_lineMasterService_lineMasterServicePlugin_CheckWeigher_checkWeigherPlugin_manualInspectionPlugin"
ManualInspectionPluginDisplay | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #11 "feature/64bits_lineMasterService_lineMasterServicePlugin_CheckWeigher_checkWeigherPlugin_manualInspectionPlugin"
MultiUserSerialMAS | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #12 "MultiUserSerialMAS MultiUserSerialMASDisplay MultiUserSerialMASTest LiddingInspectAndMark TrackingVisualization Statistics TrailViewControlLoader
MultiUserSerialMASTests | Vincent |  | Done | Done | Done | Done |  |  | Pull request #12 "MultiUserSerialMAS MultiUserSerialMASDisplay MultiUserSerialMASTest LiddingInspectAndMark TrackingVisualization Statistics TrailViewControlLoader
MultiUserSerialMASDisplay | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #12 "MultiUserSerialMAS MultiUserSerialMASDisplay MultiUserSerialMASTest LiddingInspectAndMark TrackingVisualization Statistics TrailViewControlLoader
ContainerAggregationManager | [8 empty] | Pull request #21
ContainerAggregationManagerDisplay |  |  |  |  | N/A |  |  |  | Pull request #21
DisplayComponent |  |  |  |  | N/A |  |  |  | Pull request #21
LiddingInspectAndMark | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #12 "MultiUserSerialMAS MultiUserSerialMASDisplay MultiUserSerialMASTest LiddingInspectAndMark TrackingVisualization Statistics TrailViewControlLoader
TrackingVisualization | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #12 "MultiUserSerialMAS MultiUserSerialMASDisplay MultiUserSerialMASTest LiddingInspectAndMark TrackingVisualization Statistics TrailViewControlLoader
TrackingVisualizationDisplay | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #12 "MultiUserSerialMAS MultiUserSerialMASDisplay MultiUserSerialMASTest LiddingInspectAndMark TrackingVisualization Statistics TrailViewControlLoader
Statistics | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #12 "MultiUserSerialMAS MultiUserSerialMASDisplay MultiUserSerialMASTest LiddingInspectAndMark TrackingVisualization Statistics TrailViewControlLoader
StatisticsDisplay | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #12 "MultiUserSerialMAS MultiUserSerialMASDisplay MultiUserSerialMASTest LiddingInspectAndMark TrackingVisualization Statistics TrailViewControlLoader
TrailViewControl | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #12 "MultiUserSerialMAS MultiUserSerialMASDisplay MultiUserSerialMASTest LiddingInspectAndMark TrackingVisualization Statistics TrailViewControlLoader
TrailViewControlLoader | Vincent |  | Done | Done | N/A | Done |  |  | Pull request #12 "MultiUserSerialMAS MultiUserSerialMASDisplay MultiUserSerialMASTest LiddingInspectAndMark TrackingVisualization Statistics TrailViewControlLoader
Op300 |  |  |  |  | N/A
SoftNB |  |  |  |  | N/A |  |  |  | Pull Request #22 (careful avec les struct de netburner!)
NbcCharlie |  |  |  |  | N/A |  |  |  | Pull Request #22
NBCSimulatorCharlie |  |  |  |  | N/A |  |  |  | Pull Request #22
CameraControl |  |  |  |  | N/A |  |  |  | Pull Request #22
NBController |  |  |  |  | N/A |  |  |  | Pull Request #22
VisionLib | Mikael |  | Done | Done | Done | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
StaticVisionLib | Mikael |  | Done | Done | Done | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
UtilitiesRT | pas | a faire | Done | Done | N/A | Done | Done | Done | DONE !!! car builder dans un environnement 32 bits a part.
EtherCATLibRtos | Vincent |  |  |  | N/A |  |  |  | Ne pas modifier
EtherCATLibRtos_Test | Vincent | [7 empty] | Ne pas modifier
EtherCATLib | Vincent |  |  |  | N/A |  |  |  | Ne pas modifier
EtherCATLib_Test | Vincent | [7 empty] | Ne pas modifier
OP300RT |  |  |  |  | N/A |  |  |  | Ne pas modifier restera en 32 bits Nous devons trouver une solution pour compiler en 32 bits même avec une config 64 bits.
NetBurner | Vincent |  |  |  | N/A |  |  |  | Ne pas modifier
NbcProgrammer | Vincent |  |  |  | N/A |  |  |  | Ne pas modifier
NbcProgrammerRtos | Vincent |  |  |  | N/A |  |  |  | Ne pas modifier
NbcProgrammerRtosLegacyNetwork | Vincent |  |  |  | N/A |  |  |  | Ne pas modifier
RTTools | Vincent |  |  |  | N/A |  |  |  | Ne pas modifier
CameraDetection |  |  |  |  | N/A |  |  |  | Pull request #13
TouchScreenCalibration |  |  |  |  | N/A |  |  |  | Pull request #13
BackupTool |  |  |  |  | N/A |  |  |  | Pull request #13
XRay |  |  |  |  | N/A |  |  |  | Pull request #13
IOSimulator |  |  |  |  | N/A |  |  |  | Pull request #13
ComOsmServicePlugin |  |  |  |  | N/A |  |  |  | Pull request #18
ComOsmService |  |  |  |  | N/A |  |  |  | Pull request #18
ComOsmServiceGui |  |  |  |  | N/A |  |  |  | Pull request #18
ComOsmServiceGuiTest | [8 empty] | Pull request #18
ComOsmServiceTest | [8 empty] | Pull request #18
PalletMaster | Vincent |  |  |  | N/A |  |  |  | Pull request #19
PalletMasterDisplay | Vincent |  |  |  | N/A |  |  |  | Pull request #19
PalletMasterTests | Vincent | [7 empty] | Pull request #19
Matrox | Mikael |  |  |  | N/A |  |  |  | Pull request #20
Enumerate |  |  |  |  | N/A |  |  |  | Pull request #20
RFIDPlugin |  |  |  |  | N/A |  |  |  | Bloqué par E'MindTek
RFID |  |  |  |  | N/A |  |  |  | Bloqué par E'MindTek
FFTS | Mikael | - | Done | Done | N/A | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
VisionLibTest | Mikael |  | Done | Done | Done | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"
OptelStudio | Mikael |  | Done | Done | Done | Done | Done | Done | Pull request #3 "Feature/64bits utilities genericFactory ffts fileAlterationMonitor visionLib optelStudio"

## Data
-
In Progress
Done
N/A